## REQUIREMENT MATRIX
REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER: | Devin Ward |  |  | PROJECT ID: | N/A
PROJECT SPONSOR: | UofL |  |  | PROJECT TITLE: | MDKML
REQUIREMENT INFORMATION |  |  |  |  | RELATIONSHIP TRACEABILITY
ID | CATEGORY | REQUIREMENT | PRIORITY | SOURCE | BUSINESS OBJECTIVE | DELIVERABLE(S | VERFICATION | VALIDATION
REQ-001 | Mandatory | ID: SR001- The dashboard will allow users to switch from player to team overview | High | Elaboration Spec. | Enhance user experience and flexibility | Seamless transition feature | TBD | TBD
REQ-002 | Should have | ID: SR002 – The player summary tab will allow player profiles to be created | High | Elaboration Spec. | Streamline the process of adding new player profiles to the system, ensuring comprehensive and accurate player information. | Funcitonal Player Summary Tab | TBD | TBD
REQ-003 | Mandatory | ID: SR003 – The player summary tab will allow player profiles to be edited | High | Elaboration Spec. | Enable efficient management and updating of player information, ensuring that the system reflects the most current data. | Ediitng funcitonality | TBD | TBD
REQ-004 | Mandatory | ID: SR004 – The player summary tab will allow player profiles to be deleted | High | Elaboration Spec. | Maintian data accuracy & Integrity | Image deletion functionality | TBD | TBD
REQ-005 | Should have | ID: SR005 – The player summary tab will allow player pictures to be uploaded | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Image upload functionality | TBD | TBD
REQ-006 | Should have | ID: SR006 - The player summary tab will allow player pictures to be deleted | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Image deletion funcitonality | TBD | TBD
REQ-007 | Mandatory | ID: SR007 – The player summary tab will allow information to be edited | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Editing funcitonality | TBD | TBD
REQ-008 | Should have | ID: SR008 – The player summary tab will allow information visualizations to be created | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Integration of tools within the player summary tab to create visuals | TBD | TBD
REQ-009 | Should have | ID: SR009 – The player summary tab will allow information visualization to be edited | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Editing funcitonality | TBD | TBD
REQ-010 | Should have | ID: SR010 – The player summary tab will allow visualizations to be deleted. | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Feature to enable to the deletion of visualiztions | TBD | TBD
REQ-011 | Mandatory | ID: SR011 – The game/career statistics tab will allow information to be edited | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Editing capabilites | TBD | TBD
REQ-012 | Mandatory | ID: SR012 – The strength training tab will allow information to be edited | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Editing capabilites | TBD | TBD
REQ-013 | Mandatory | ID: SR013 – The strength training tab will allow players’ workout history to be deleted | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Feature allowing for the deletion of workout history | TBD | TBD
REQ-014 | Should have | ID: SR014 – The strength training tab will allow players’ workout history to be formatted | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Functionality to format workout history | TBD | TBD
REQ-015 | Should have | ID: SR015 – The strength training tab will allow information visualizations to be created | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Tools for creating viduals | TBD | TBD
REQ-016 | Should have | ID: SR016 – The strength training tab will allow information visualization to be edited | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Editing capabilities | TBD | TBD
REQ-017 | Should have | ID: SR017 – The strength training tab will allow visualizations to be deleted | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Feature enabilig the dleetion of visualiztions | TBD | TBD
REQ-018 | Mandatory | ID: SR018 – The medical tab will allow information to be edited | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Editing features within the medical tab | TBD | TBD
REQ-019 | Mandatory | ID: SR019 – The medical tab will allow players’ medical information to be uploaded | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Image upload functionality | TBD | TBD
REQ-020 | Mandatory | ID: SR020 – The medical tab will allow players’ medical information to be deleted | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Feature allowing for the deelation of players medical information | TBD | TBD
REQ-021 | Mandatory | ID: SR021 – The medical tab will allow player’s medical status to be created | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Feature allowing for the creation of medical data | TBD | TBD
REQ-022 | Mandatory | ID: SR022 – The medical tab will allow player’s medical status to be edited | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Editing cpaabilitiew for player medical status | TBD | TBD
REQ-023 | Mandatory | ID: SR023 – The medical tab will allow player’s medical status to be deleted | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Deletion capabilities for player medical data | TBD | TBD
REQ-024 | Should have | ID: SR024 – The medical tab will allow information visualizations to be created | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Tools for creatingg viduals | TBD | TBD
REQ-025 | Should have | ID: SR025 – The medical tab will allow information visualization to be edited | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Editing capabilites | TBD | TBD
REQ-026 | Should have | ID: SR026 – The medical tab will allow visualizations to be deleted. | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Deletion capabilities for player medical data | TBD | TBD
REQ-027 | Mandatory | ID: SR027 – The nutrition tab will allow information to be edited | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Editing features in the nution tab | TBD | TBD
REQ-028 | Should have | ID: SR028 – The nutrition tab will allow information visualizations to be created | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Tools in the nutrion tab for creasitng visuals | TBD | TBD
REQ-029 | Should have | ID: SR029 – The nutrition tab will allow information visualization to be edited | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Editing capabilites | TBD | TBD
REQ-030 | Should have | ID: SR030 – The nutrition tab will allow visualizations to be deleted. | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Features enabiling thr delation of visuals | TBD | TBD
REQ-031 | Mandatory | ID: SR031 – The practice data tab will allow information to be edited | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Editing features in the practice data tab | TBD | TBD
REQ-032 | Should have | ID: SR032 – The practice data tab will allow visualizations to be created | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Tools in the practice data tab for creating visuals | TBD | TBD
REQ-033 | Should have | ID: SR033 – The practice data tab will allow visualizations to be edited. | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Editing cpaabilites for informaiton visualiztions | TBD | TBD
REQ-034 | Should have | ID: SR034 - The practice data tab will allow visualizations to be deleted | Low | Elaboration Spec. | Maintian data accuracy & Integrity | Featuerrs enabling the deletion of vislauztions within the practice data tab | TBD | TBD
REQ-035 | Mandatory | ID: SR035 – The comparisons’ tab will allow information to be edited | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Editing features within the comparisions tab to modify comparison realted information | TBD | TBD
REQ-036 | Mandatory | ID: SR036 – The comparisons’ tab will allow access to information from other tabs | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Integraiton feature al;lpowing access to information from other tabs | TBD | TBD
REQ-037 | Mandatory | ID: SR037 – The comparisons’ tab will allow tab comparisons to be created | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Feature enabling the creation of comparions | TBD | TBD
REQ-038 | Mandatory | ID: SR038 – The comparisons’ tab will allow tab comparisons to be edited | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Editing capabilites | TBD | TBD
REQ-039 | Mandatory | ID: SR039 – The comparisons’ tab will allow tab comparisons to be deleted | Medium | Elaboration Spec. | Maintian data accuracy & Integrity | Deletion capabilites | TBD | TBD
REQ-040 | Mandatory | ID: SR040– Data input will allow information to be edited | High | Elaboration Spec. | Maintian data accuracy & Integrity | Inertactive data input forms | TBD | TBD
REQ-041 | Mandatory | ID: SR041 – Data input will allow data to be imported | High | Elaboration Spec. | Maintian data accuracy & Integrity | Functionality to import external data | TBD | TBD
REQ-042 | Mandatory | ID: SR042 – Data input will allow data to be exported | High | Elaboration Spec. | Maintian data accuracy & Integrity | Export features to extract data | TBD | TBD
REQ-043 | Mandatory | ID: SR043– Data input will allow manual data entry | High | Elaboration Spec. | Maintian data accuracy & Integrity | User frinedly interface to allow for manual input of data | TBD | TBD
REQ-044 | Mandatory | ID: SR044 – Data input will allow automatic data entry | High | Elaboration Spec. | Maintian data accuracy & Integrity | Automated process that will enable systems to receive and process data automatically | TBD | TBD
REQ-045 | Mandatory | ID: SR045 – Information on tabs will be viewable by user | High | Elaboration Spec. | Maintian data accuracy & Integrity | User interface design to ensure that all information on tabs is presented clearly. | TBD | TBD

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
REQUIREMENT ID
Give each requirement a unique identifier or reference so that it can be easily traced throughout the project life-cycle.
CATEGORY
Provide a category for the requirement typical categories are: functional, non-functional, usability, security, performance, maintainability etc.
REQUIREMENT
Describe the requirement that needs to be met by the project. The requirement might be a product, some product functionality, a service, or a result.
PRIORITY
Provide a priority for the requirement. For example, mandatory, should have, nice to have or high, medium, low.
SOURCE
Enter the name of the stakeholder that identified the requirement.
BUSINESS OBJECTIVE
Document the business objective that this requirement will meet or help to meet. The business objective will come from the project charter or the Project business Case.
DELIVERABLE(S)
List the deliverable or deliverables that will make up this requirement.
VERIFICATION
Explain how you will test that the requirement is completed satisfactorily. For example 99.9% uptime for user acceptance of software.
VALIDATION
Explain how the requirement will be validated or tested. This will often be via user acceptance testing, but it might also be by the achievement of a milestone or perhaps by the completion of a key performance indicator.
This template was provided by
https://www.stakeholdermap.com/

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN STATUS FIELDS
Default settings
We have not set any drop down menus, as it is likely that most projects will have different priorities and categories.
How to create a drop down menu
Click on Data tab > Data Validation > Settings > List
In the Source field enter the menu items separated by a comma.
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings > List
ADDITIONAL FIELDS YOU MIGHT WANT TO ADD
Supplier - On projects with multiple suppliers you may want to add a field to note the supplier responsible.
WBS ID - Add WBS ID so that the requirement can be linked to the Work Breakdown Structure and project schedule.
Test case ID - Later in the project you may want to link the requirement to the test cases that will be used to
check that the requirement meets the business objective.
This template was provided by
https://www.stakeholdermap.com/